{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":151,"n_cols":7,"rows_kept":151,"merged":[[0,0,0,6]]}
["2026年上半年城市道路挖掘计划表（清城区）"]
["序号","单位","施工路段","施工内容","计划开工日期","计划完工日期","备注"]
[1,"清远清城供电局","湖城大道","顶管，开挖，埋管，电缆井制作","2025-01-01","2025-03-30","洲心街道"]
[2,"清远清城供电局","人民东路","顶管，开挖，埋管，电缆井制作","2025-01-01","2025-03-30","洲心街道"]
[3,"清远清城供电局","凤翔中路","顶管，开挖，埋管，电缆井制作","2025-01-01","2025-06-30","洲心街道"]
[4,"清远清城供电局","广清大道、龙国大道","顶管，开挖，埋管，电缆井制作","2025-01-01","2025-06-30","龙塘镇"]
[5,"清远清城供电局","凤翔中路、创兴大道","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-02-10","横荷街道"]
[6,"清远清城供电局","广清大道","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-02-10","横荷街道"]
[7,"清远清城供电局","广清大道","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-05-30","横荷街道"]
[8,"清远清城供电局","锦绣西路","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-02-10","横荷街道"]
[9,"清远清城供电局","创兴五路、建设三路","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-01-30","横荷街道"]
[10,"清远清城供电局","德宝东路、建设一路","顶管，开挖，埋管，电缆井制作","2025-01-06","2025-04-30","横荷街道"]
[11,"清远清城供电局","东城附城大道、金碧路、莲蟠路、凤翔北路、海逸路","顶管，开挖，埋管，电缆井制作","2025-01-01","2025-06-30","东城街道"]
[12,"清远市清城区防汛防旱防风服务中心","环城东路奥体段、沿江中路、聚龙街、聚福街","新建雨污水管，管道清淤、非开挖修复，新建排水沟","2025-12-20","2026-03-31","东城街道"]
[13,"清远市清城区防汛防旱防风服务中心","环城路","开挖，埋管，清淤","2026-05-01","2026-05-31","凤城街道"]
[14,"清远市清城区防汛防旱防风服务中心","松鹤大街、城西北路、","开挖，埋管，清淤、分流井","2026-05-20","2026-06-30","凤城街道"]
[15,"清远市清城区防汛防旱防风服务中心","麦围大街和东湖路相交处","清淤","2026-02-25","2026-03-20","凤城街道"]
[16,"清远市清城区防汛防旱防风服务中心","环城西路和西门塘横街相交处","开挖，埋管，清淤","2026-04-15","2026-05-05","凤城街道"]
[17,"清远市清城区防汛防旱防风服务中心","环城二路一巷","开挖，埋管，清淤","2026-03-25","2026-04-20","凤城街道"]
[18,"清远市清城区防汛防旱防风服务中心","西环雅群东门前路、环城一路和西门塘直街相交处","开挖，埋管，清淤","2026-02-25","2026-03-20","凤城街道"]
[19,"清远市清城区防汛防旱防风服务中心","清沙大道","开挖，埋管、泵站","2026-01-01","2026-01-30","凤城街道"]
[20,"清远市清城区防汛防旱防风服务中心","凤翔中路、建设四路、富强路、锦绣路、107国道（广清大道）、创兴路","凤翔中路百加社区雨污接口","2026-04-10","2026-06-10","横荷街道"]
[21,"清远市清城区防汛防旱防风服务中心","凤翔中路、建设四路、富强路、锦绣路、108国道（广清大道）、创兴路","建设四路顶管","2026-04-20","2027-02-20","横荷街道"]
[22,"清远市清城区防汛防旱防风服务中心","凤翔中路、建设四路、富强路、锦绣路、109国道（广清大道）、创兴路","富强路顶拉管接口","2026-03-15","2026-05-10","横荷街道"]
[23,"清远市清城区防汛防旱防风服务中心","凤翔中路、建设四路、富强路、锦绣路、110国道（广清大道）、创兴路","绵绣路顶拉管接口","2026-06-20","2026-08-31","横荷街道"]
[24,"清远市清城区防汛防旱防风服务中心","锦霞西路南侧末端、锦霞西路上下阮、富强路鸡啼岭、静福路与峡山西路路口、燕湖大道北侧","开挖、新建管道铺设、顶管、井制作","2025-09-01","2026-01-31","横荷街道、洲心街道"]
[25,"清远市清城区防汛防旱防风服务中心","银泉北路高度悦酒店门口辅路","箱涵清淤","2025-11-17","2025-12-28","横荷街道、洲心街道"]
[26,"清远市清城区防汛防旱防风服务中心","人民路与铁塔路交汇环岛南侧大木洲河岸道路","河道清淤","2025-11-19","2025-12-18","横荷街道、洲心街道"]
[27,"清远市清城区防汛防旱防风服务中心","清城区清晖中路朝南燕湖汇对面","新建智能分流井","2025-12-10","2026-03-23","横荷街道、洲心街道"]
[28,"清远市清城区防汛防旱防风服务中心","清晖路与人民东路交叉口","W159-W161，W162-W164开挖新建管道铺设、井制作","2025-12-20","2026-02-08","洲心街道"]
[29,"清远市清城区防汛防旱防风服务中心","青联路与人民东路交叉口","Y324-Y325开挖、新建管道铺设、井制作","2025-12-20","2026-02-08","洲心街道"]
[30,"清远市清城区防汛防旱防风服务中心","塘坦路与人民东路交叉口","W148-W150开挖、新建管道铺设、井制作","2025-12-20","2026-02-08","洲心街道"]
[31,"清远市清城区防汛防旱防风服务中心","连水路与人民东路交叉口","Y322-Y323开挖、新建管道铺设、井制作","2025-12-20","2026-02-08","洲心街道"]
[32,"清远市清城区防汛防旱防风服务中心","洲心路与人民东路交叉口","W151-W157,W155-W158开挖、新建管道铺设、井制作","2025-12-20","2026-02-08","洲心街道"]
[33,"清远市清城区防汛防旱防风服务中心","南大街","W1-17,Y11-Y27开挖、新建管道铺设、井制作","2026-03-01","2026-06-29","洲心街道"]
[34,"清远市清城区防汛防旱防风服务中心","人民西路辅路三角幼儿园附近","Y158-Y160开挖、新建管道铺设、井制作","2026-03-01","2026-04-10","洲心街道"]
[35,"清远市水务投资集团","红旗西街","顶管，开挖，埋管","2026-03-01","2026-03-30","东城街道办"]
[36,"清远市水务投资集团","凤翔北路(旅游大道至职教一路）","顶管，开挖，埋管","2026-03-01","2026-03-30","东城街道办"]
[37,"清远市水务投资集团","凤翔北路(红旗西街至职教一路）","顶管，开挖，埋管","2026-01-01","2026-01-30","东城街道办"]
[38,"清远市水务投资集团","清晖北路（大学东路至职教二路）","顶管，开挖，埋管","2026-01-01","2026-01-30","东城街道办"]
[39,"清远市水务投资集团","清晖北路（清飞路至沿江路）","顶管，开挖，埋管","2026-01-10","2026-02-18","东城街道办"]
[40,"清远市水务投资集团","学文路","顶管，开挖，埋管","2026-03-01","2026-04-10","东城街道办"]
[41,"清远市水务投资集团","环城东路","顶管，开挖，埋管","2026-01-05","2026-01-30","东城街道办"]
[42,"清远市水务投资集团","新城路","顶管，开挖，埋管","2026-03-03","2026-05-06","洲心街道"]
[43,"清远市水务投资集团","人民东路","顶管，开挖，埋管","2026-03-01","2026-04-10","洲心街道"]
[44,"清远市水务投资集团","清远大道","顶管，开挖，埋管","2026-03-03","2026-05-06","横荷街道"]
[45,"清远市水务投资集团","创兴大道（建设二路至建设三路段）","顶管，开挖，埋管","2026-03-20","2026-04-18","高新区横荷街道"]
[46,"清远市水务投资集团","建设三路（创兴大道至技师学院）","顶管，开挖，埋管","2026-04-01","2026-04-20","高新区横荷街道"]
[47,"清远市水务投资集团","创兴二路（建设二路向西延长200米）","顶管，开挖，埋管","2026-01-01","2026-01-20","高新区横荷街道"]
[48,"清远市水务投资集团","华兴二路（建设一路至建设二路）","顶管，开挖，埋管","2026-01-15","2026-02-03","高新区横荷街道"]
[49,"清远市水务投资集团","建设一路（创兴三路至德宝东路段）、德宝东路段","顶管，开挖，埋管","2026-01-01","2026-01-30","高新区横荷街道"]
[50,"清远市水务投资集团","百加大街路段","顶管，开挖，埋管","2025-12-20","2026-02-09","洲心街道"]
[51,"清远市水务投资集团","峡江西路（广清大道至海伦春天南门路段）","顶管，开挖，埋管","2025-12-20","2026-01-18","洲心街道"]
[52,"清远市水务投资集团","永安南路（半环北路至燕湖大道）","顶管，开挖，埋管","2026-01-01","2026-03-28","洲心街道"]
[53,"清远市水务投资集团","广清大道（连江路至清远大道）","顶管，开挖，埋管","2026-01-01","2026-05-11","洲心街道"]
[54,"清远市水务投资集团","锦锈西路（广清大道至富强路段)","顶管，开挖，埋管","2026-03-03","2026-05-06","洲心街道"]
[55,"清远市水务投资集团","连江西路（永安北路至国泰路）","顶管，开挖，埋管","2026-03-03","2026-04-16","洲心街道"]
[56,"清远市水务投资集团","国泰路（连江西路至凤鸣西路段)","顶管，开挖，埋管","2026-03-10","2026-04-23","洲心街道"]
[57,"清远市水务投资集团","北环半路（广清大道至永安北路路段）","顶管，开挖，埋管","2026-01-13","2026-02-11","洲心街道"]
[58,"清远市水务投资集团","清远大道（广清大道至高速路）","顶管，开挖，埋管","2026-03-03","2026-06-30","洲心街道"]
[59,"清远市水务投资集团","凤鸣东路（北江二路至广清大道段）","顶管，开挖，埋管","2026-03-03","2026-04-21","洲心街道"]
[60,"清远市水务投资集团","半环北路东段（广清大道至银泉北路段）","顶管，开挖，埋管","2026-04-10","2026-05-29","洲心街道"]
[61,"清远市水务投资集团","北江一路（清晖北路至金海湾豪庭）","顶管，开挖，埋管","2026-05-01","2026-06-19","洲心街道"]
[62,"清远市水务投资集团","人民路北段（连江路至广信花园段）","顶管，开挖，埋管","2026-03-03","2026-04-16","洲心街道"]
[63,"清远市水务投资集团","人民路北段（广信花园至铁塔路段）","顶管，开挖，埋管","2026-04-17","2026-05-31","洲心街道"]
[64,"清远市水务投资集团","人民路南段（铁塔路至静福路）","顶管，开挖，埋管","2026-04-01","2026-04-30","洲心街道"]
[65,"清远市水务投资集团","人民路南段（银泉北路至连江路）","顶管，开挖，埋管","2026-05-01","2026-05-25","洲心街道"]
[66,"清远市水务投资集团","人民路南段（连江路至广清大道）","顶管，开挖，埋管","2026-05-26","2026-06-19","洲心街道"]
[67,"清远市水务投资集团","凤翔大道（清远大道至人民路）","顶管，开挖，埋管","2026-05-01","2026-07-29","洲心街道"]
[68,"清远市水务投资集团","北江三路（永安北路至清远海关）","顶管，开挖，埋管","2026-03-03","2026-03-27","洲心街道"]
[69,"清远市水务投资集团","永安北路（北江三路至连江西路）","顶管，开挖，埋管","2026-03-28","2026-04-26","洲心街道"]
[70,"清远市水务投资集团","连江西路（永安北路至连江路）","顶管，开挖，埋管","2026-04-27","2026-05-26","洲心街道"]
[71,"清远市水务投资集团","连江路（人民路至鹿鸣路段）","顶管，开挖，埋管","2026-05-27","2026-06-25","洲心街道"]
[72,"清远市水务投资集团","连江路（鹿鸣路段至凤鸣路段）","顶管，开挖，埋管","2026-06-01","2026-06-30","洲心街道"]
[73,"清远市水务投资集团","连江路（凤鸣路至滨江路段）","顶管，开挖，埋管","2026-07-01","2026-07-30","洲心街道"]
[74,"清远市水务投资集团","清远大道（广清大道至凤翔大道）","顶管，开挖，埋管","2026-06-20","2026-08-03","洲心街道"]
[75,"清远港华燃气有限公司","清远市凤翔北路与职教一路交界","清远市职教一路西延线市政中压燃气管道工程","2025-03-10","6月31日","东城街道"]
[76,"清远港华燃气有限公司","清远市东城东岗路","清远市东城东岗路市政中压燃气管道工程","2025-04-05","2025-05-15","东城街道"]
[77,"清远港华燃气有限公司","清远市富强路","清远市富强路大唐京品市政中压燃气管道工程","2025-03-20","2025-04-20","横荷街道"]
[78,"清远港华燃气有限公司","清远市广清大道（人民路路口、峡江西路路口、创兴大道路口、龙塘环城东至龙国道、银英公路路口）","清远市广清大道快速化迁改","2025-01-05","2025-12-15","洲心、横荷、龙塘（分段施工）"]
[79,"清远港华燃气有限公司","清远市石角镇梦湖路（美林湖大道-湖岸东路）","清远市石角镇梦湖路（X844）市政中压燃气管道工程","2026-03-05","2026-06-25","石角"]
[80,"清远港华燃气有限公司","清城区石角镇灵洲大道、灵康路","石角镇灵康路长盈初记有限公司市政中压燃气管道工程","2026-01-01","2026-02-11","石角"]
[81,"清远港华燃气有限公司","清城区石角镇金康大街","石角镇金康大街（新联达花园段）市政燃气管道工程","2025-01-20","2026-03-10","石角"]
[82,"清远港华燃气有限公司","清城区石角镇金康大道","清远市石角镇金康大街（明记菜馆段）市政燃气管道工程","2026-01-20","2025-02-10","石角"]
[83,"清远港华燃气有限公司","清城区石角镇（清三公路）","石角镇金保利三期市政中压燃气管道工程","2026-03-05","2026-03-31","石角"]
[84,"清远港华燃气有限公司","清城区银盏泰基路","清远市泰基路（与广清大道交界餐饮店段）市政中压燃气管道工程","2025-01-05","2025-02-12","龙塘"]
[85,"清远港华燃气有限公司","清城区建设三路","建设三路（清远市青鸟职业技术学院段）市政中压燃气管道工程","2025-01-15","2025-02-10","横荷街道"]
[86,"清远港华燃气有限公司","清城区建设四路","清远市高新区建设四路（创兴二路至创兴三路）燃气管道连接工程","2025-03-15","2025-05-15","横荷街道"]
[87,"清远港华燃气有限公司","清城区龙塘镇（广清大道）","清远市恒通裕科技产业园市政中压燃气管道工程","2025-03-15","2025-06-12","龙塘"]
[88,"清远港华燃气有限公司","高新区百加大街、永利一街","百加大街、永利一街市政燃气管道工程","2025-01-01","2025-02-06","横荷街道"]
[89,"清远港华燃气有限公司","华清工业园内","华清工业园中再生华阳铝业有限公司\n（主阀ZF206）","2026-05-10","2026-06-10","石角"]
[90,"清远港华燃气有限公司","省道S269界牌小学对面","阀门维护开挖省道S269界牌小学对面（主阀ZF211）","2026-05-10","2026-06-10","石角"]
[91,"清远港华燃气有限公司","省道S269界牌小学斜对面","阀门维护开挖省道S269界牌小学斜对面（主阀ZF212）","2026-05-10","2026-06-10","石角"]
[92,"清远港华燃气有限公司","省道S269尚高洁具附近","阀门维护开挖省道S269清远尚高洁具有限公司右侧30左右（主阀ZF221）","2026-05-10","2026-06-10","石角"]
[93,"清远港华燃气有限公司","省道S269鑫叶材料附近","阀门维护开挖省道S269清远市鑫叶新型材料有限公司门口（主阀ZF221）","2026-05-10","2026-06-10","石角"]
[94,"清远港华燃气有限公司","清城区石龙大道","阀门维护开挖石龙大道桐心百货超市门口（主阀ZF238）","2026-05-10","2026-06-10","石角"]
[95,"清远港华燃气有限公司","清城区石角清三公路","阀门维护开挖清三公路超限检测出口附近（主阀ZF621）","2026-05-10","2026-06-10","石角"]
[96,"清远港华燃气有限公司","清远市北江一路（铁塔路路口）","清远市北江一路（铁塔路路口）燃气管改造工程","2025-01-05","2025-02-05","洲心街道"]
[97,"清远港华燃气有限公司","东城大学西路(喜洋洋罄苑南门）","清远市东城喜洋洋罄苑小区市政中压燃气管道工程","2025-03-15","2025-04-15","东城街道"]
[98,"清远港华燃气有限公司"," 清三公路旁","横荷镇远光电缆有限公司市政中压燃气管道工程","2025-03-01","2025-06-30","横荷街道"]
[99,"清远港华燃气有限公司","清远市永安路（峡江西路-秀丽路）","清远市永安路（峡江西路-秀丽路）市政中压燃气管道工程","2025-01-06","2025-02-06","横荷街道"]
[100,"清远港华燃气有限公司","清远市下廓街（泰青青泰融合菜段）","清远市下廓街（泰青青泰融合菜段）市政中压燃气管道工程","2025-01-10","2025-02-10","凤城街道"]
[101,"清远港华燃气有限公司","清远市人民东路（黄其大排档）","清远市人民东路（黄其大排档）市政中压燃气管道工程","2025-01-01","2025-01-10","洲心街道"]
[102,"清远港华燃气有限公司","清远市汇祥路（汇祥楼段）","清远市汇祥路（汇祥楼段）市政中压燃气管道工程","2025-01-05","2025-01-30","凤城街道"]
[103,"清远港华燃气有限公司","清远市学文路（悦江南小区段）","清远市学文路（悦江南小区段）市政中压燃气管道工程","2025-01-10","2025-01-30","东城街道"]
[104,"清远港华燃气有限公司","清远市广泰商业街（俊龙楼段）","清远市广泰商业街（俊龙楼段）市政中压燃气管道工程","2025-01-10","2025-02-10","洲心街道"]
[105,"清远港华燃气有限公司","清远市东城锦兴路（客乡情段）","清远市东城锦兴路（客乡情段）市政中压燃气管道工程","2025-01-05","2025-02-05","东城街道"]
[106,"清远港华燃气有限公司","清远市永安街（金御大厦段）","清远市永安街（金御大厦段）市政中压燃气管道工程","2025-02-25","2025-03-25","洲心街道"]
[107,"清远港华燃气有限公司","清远市滨江路（云贵川烧烤店段）","清远市滨江路（云贵川烧烤店段）市政中压燃气管道工程","2025-01-15","2025-02-10","洲心街道"]
[108,"清远港华燃气有限公司","广泰商业街（连州金全大排档段）","清远市广泰商业街（连州金全大排档段）市政中压燃气管道工程","2025-01-15","2025-02-10","洲心街道"]
[109,"清远港华燃气有限公司","清远市东城大道（超然一品段）","清远市东城大道（超然一品段）市政中压燃气管道工程","2025-01-10","2025-02-10","东城街道"]
[110,"清远港华燃气有限公司","清远市银泉南路（城际嘉园段）","清远市银泉南路（城际嘉园段）市政中压燃气管道工程","2025-01-01","2025-01-07","洲心街道"]
[111,"清远港华燃气有限公司","清远市通源北街（李倩文个人厨房段）","清远市通源北街（李倩文个人厨房段）市政中压燃气管道工程","2025-01-05","2025-01-30","洲心街道"]
[112,"清远港华燃气有限公司","清远市下廓街（阿香连洲大排档段）","清远市下廓街（阿香连洲大排档段）市政中压燃气管道工程","2025-01-05","2025-01-30","凤城街道"]
[113,"清远港华燃气有限公司","清远市西门塘直街（秤心如意食坊段）","清远市西门塘直街（秤心如意食坊段）市政中压燃气管道工程","2025-01-10","2025-02-10","凤城街道"]
[114,"清远港华燃气有限公司","清远市东门塘路（白玉鼎冬瓜盅段）","清远市东门塘路（白玉鼎冬瓜盅段）市政中压燃气管道工程","2025-01-01","2025-01-06","凤城街道"]
[115,"清远港华燃气有限公司","清远市海逸路（敏捷东城水岸A区三期段）","清远市海逸路（敏捷东城水岸A区三期段）市政中压燃气管道工程","2025-01-01","2025-01-07","东城街道"]
[116,"清远港华燃气有限公司","清远市通源南街（嘉家粽段）","清远市通源南街（嘉家粽段）市政中压燃气管道工程","2025-01-06","2025-01-25","洲心街道"]
[117,"清远港华燃气有限公司","清城区峡江西路（超然一品烧餐厅段）","清远市清城区峡江西路（超然一品烧餐厅段）市政中压燃气管道工程","2025-01-10","2025-02-10","洲心街道"]
[118,"清远港华燃气有限公司","清城区西门塘直街（金晖雅居段）","清远市清城区西门塘直街（金晖雅居段）市政中压燃气管道工程","2025-02-25","2025-03-25","凤城街道"]
[119,"清远港华燃气有限公司","清远市东门塘路（头号外婆餐饮段）","清远市东门塘路（头号外婆餐饮段）市政中压燃气管道工程","2025-03-05","2025-04-05","凤城街道"]
[120,"清远港华燃气有限公司","清城区松涛大街（周杨传统竹升面馆段）","清远市清城区松涛大街（周杨传统竹升面馆段）市政中压燃气管道工程","2025-01-15","2025-02-05","凤城街道"]
[121,"清远港华燃气有限公司","清远市通源南街（艺龙广告装饰段）","清远市通源南街（艺龙广告装饰段）市政中压燃气管道工程","2025-02-25","2025-03-25","洲心街道"]
[122,"清远港华燃气有限公司","清远市铁塔路（大东北饺子馆段）","清远市铁塔路（大东北饺子馆段）市政中压燃气管道工程","2025-01-15","2025-02-05","洲心街道"]
[123,"清远港华燃气有限公司","清远市人民东路（高妹私房菜、煲煲乐农庄段）","清远市人民东路（高妹私房菜、煲煲乐农庄段）市政中压燃气管道工程","2025-01-15","2025-02-05","洲心街道"]
[124,"清远港华燃气有限公司","清远市清源西路（雨虹瓷胶砖店段）","清远市清源西路（雨虹瓷胶砖店段）市政中压燃气管道工程","2025-03-10","2025-04-10","洲心街道"]
[125,"清远港华燃气有限公司","清远市富强路（寻味顺德段）","清远市富强路（寻味顺德段）市政中压燃气管道工程","2025-01-01","2025-01-12","横荷街道"]
[126,"清远市自来水工程有限公司","洲心街道3、4号区","塌陷点修复","2025-01-03","2025-01-15","洲心街道"]
[127,"清远市自来水工程有限公司","清远大道","塌陷点修复","2025-01-10","2025-02-12","横荷街道"]
[128,"清远市自来水工程有限公司","广清大道（半环北路-峡江西路）","易涝点整治","2025-01-02","2025-06-30","洲心街道"]
[129,"清远市自来水工程有限公司","银泉北路","易涝点整治","2025-01-18","2025-02-01","洲心街道"]
[130,"清远市自来水工程有限公司","富强路","易涝点整治","2025-01-20","2025-04-30","洲心街道"]
[131,"清远市自来水工程有限公司","明安路","易涝点整治","2025-01-15","2025-02-05","洲心街道"]
[132,"清远市自来水工程有限公司","连江路","塌陷点修复","2025-02-10","2025-04-01","洲心街道"]
[133,"清远市自来水工程有限公司","连江西路","塌陷点修复","2025-02-28","2025-04-01","洲心街道"]
[134,"清远市自来水工程有限公司","人医箱涵","提升检查井","2025-01-02","2025-02-01","洲心街道"]
[135,"清远市自来水工程有限公司","人民二路","塌陷点修复","2025-03-15","2025-04-20","洲心街道"]
[136,"清远市自来水工程有限公司","凤鸣路","塌陷点修复","2025-01-20","2025-02-10","洲心街道"]
[137,"清远市自来水工程有限公司","凤城大桥","增设雨水井","2025-01-25","2025-02-10","洲心街道"]
[138,"清远市自来水工程有限公司","北江三路","塌陷点修复","2025-02-01","2025-02-10","洲心街道"]
[139,"清远市自来水工程有限公司","二号区通源北街","塌陷点修复","2025-03-05","2025-03-20","凤城街道"]
[140,"清远市自来水工程有限公司","下郭二街","塌陷点修复","2025-04-01","2025-04-10","凤城街道"]
[141,"清远市自来水工程有限公司","下郭街","塌陷点修复","2025-04-10","2025-05-01","凤城街道"]
[142,"清远市自来水工程有限公司","暑光路","塌陷点修复","2025-04-20","2025-05-10","凤城街道"]
[143,"清远市自来水工程有限公司","西门塘直街","塌陷点修复","2025-05-01","2025-05-15","凤城街道"]
[144,"清远市自来水工程有限公司","西门塘横街","塌陷点修复","2025-05-10","2025-05-30","凤城街道"]
[145,"清远市自来水工程有限公司","古龙路","塌陷点修复","2025-05-20","2025-06-01","凤城街道"]
[146,"清远市自来水工程有限公司","松鹤西街","塌陷点修复","2025-06-01","2025-06-10","凤城街道"]
[147,"清远市自来水工程有限公司","飞来南路","塌陷点修复","2025-06-10","2025-06-20","凤城街道"]
[148,"清远市自来水工程有限公司","飞来北路","塌陷点修复","2025-06-15","2025-06-30","凤城街道"]
[149,"清远市自来水工程有限公司","西环雅苑东门","塌陷点修复","2025-06-25","2025-06-30","凤城街道"]